## Sheet1
Priority | Milestone | Sub Milestone | Task | No of Hours | Comments
1 | Landing Page | UX Design
Front End
|  | Project Set up |  | 16
|  |  | HTML retrofitting | 16
2 | Listing of Services
|  | Service Listing Page | UX Design
Front End
Elderly Dashboard
UX Design
Front End
|  |  | HTML retrofitting | 16
|  |  | Elderly Register | 16
|  |  | Elderly Login | 16
|  |  | Search/Filter | 16
|  |  | Request | 8
|  |  | Message | PARKED | Taking it up with Community
|  |  | Review and rate | 24
|  |  | Service use tracker | 16
3 | Information Repository | UX Design
Front End
|  |  | HTML retrofitting | 16
|  |  | Comment | 16
|  |  | Rate | 16
|  |  | Share | 12
|  |  | Bookmark | 12
|  | Add Article |  | 16
|  | Bookmarks |  | 16
|  | Notification |  | PARKED | Taking it up with Community
Artilcle Comments
Message
4 | Products
UX Design
Front End
|  | HTML retrofitting |  | 16
|  | Product List |  | 16
|  | Product Details |  | 16
|  | Search/Filter |  | 16
5 | Volunteers
UX Design
Front End
|  | List |  | 16
|  | View Profile |  | 16
|  | Message |  | PARKED | Taking it up with Community
|  | Request Service |  | 12
|  | Rate |  | 12
|  | Review |  | 24
|  | Service Tracker |  | 12
|  | Elderly Volunteers |  | PARKED | Need more info
6 | Community
UX Design
Front End
|  | HTML retrofitting |  | 32
|  | User Profile |  | 24
|  | Search Users |  | 24
|  | Discussion Forum |  | PARKED | How is this different from groups?
|  | Message |  | 32
|  | Friends |  | 32
|  | Family |  | 24
|  | Feeds |  | 80
|  | Abuse Reports |  | 12
|  | Role |  | PARKED | Need more info
7 | Groups & Events
UX Design
Front End
|  | HTML retrofitting |  | 32
|  | Create Group |  | 16
|  | Post |  | 24
|  | Search |  | 18
|  | Create Event |  | 16
|  | Post |  | 16
|  | Search |  | 18
8 | Service Provider dashboard
UX Design
Front End
HTML retrofitting
Add Service
Add Product
Manage Service & products
Message
9 | Volunteer dashboard
10 | Admin Module